## Project Overview
Project Name | DevSolve
Objective | To resolve unanswered Stack Overflow queries by crowdsourcing solutions.
Tech Stack | Next.js (Frontend), Node.js + Express.js (Backend), PostgreSQL (Database), Puppeteer/Cheerio (Scraping), NextAuth.js (Authentication)
Core Features | Scraping, Categorization, Answer Contribution, Voting System, Authentication
Deployment Plan | Frontend - Vercel, Backend - Render/Fly.io
Expected Completion | 15 Days
Day | Task | Status
1 | Project Setup (Frontend, Backend, Database)INSTALATION | Done
2 to 3 | Scraping Stack Overflow (Puppeteer/Cheerio) | Done
4 to 5 | API Development (Questions Endpoint) | Done
6 | OAuth Authentication Setup (GitHub, Google) | Ongoing
7 | User System & Secure Routes
8 | UI for Viewing Questions
9 | Answer Contribution System
10 | Storing & Fetching Answers
11 | Displaying Answers in UI
12 | Voting System Implementation
13 | Sorting Answers by Votes
14 | Testing & Debugging
15 | Deployment & Documentation

## Development Roadmap
Day | Task | Status
1 | Initialize GitHub repo, setup Next.js & Express.js, configure PostgreSQL | Pending
2 | Setup Puppeteer/Cheerio for scraping, test initial data extraction | Pending
3 | Optimize scraping logic, store questions in PostgreSQL | Pending
4 | Develop API to fetch scraped questions from database | Pending
5 | Implement API to filter & categorize questions | Pending
6 | Integrate NextAuth.js for GitHub/Google authentication | Pending
7 | Create user model & restrict API access to authenticated users | Pending
8 | Develop frontend UI for listing & viewing questions | Pending
9 | Implement answer submission feature & backend endpoint | Pending
10 | Store and fetch answers from database | Pending
11 | Display answers under questions, implement UI improvements | Pending
12 | Develop upvote/downvote feature in backend | Pending
13 | Integrate voting functionality into frontend | Pending
14 | Run end-to-end testing, fix bugs, optimize performance | Pending
15 | Deploy to Vercel (frontend) & Render/Fly.io (backend), finalize documentation | Pending

## Database Schema
Table Name | Columns | Description
users | id, name, email, provider, provider_id, profile_picture, created_at | Stores user details
questions | id, title, link, votes, tags, created_at | Stores scraped Stack Overflow questions
answers | id, user_id, question_id, content, created_at | Stores user-submitted answers
votes | id, user_id, answer_id, vote_type (up/down), created_at | Stores votes on answers

## Testing Checklist
Feature | Test Case | Status
Authentication | User can log in with GitHub/Google | Pending
Scraping | Questions are fetched correctly | Pending
Answer Submission | Users can post an answer | Pending
Voting | Upvotes/downvotes update correctly | Pending
API Security | Unauthenticated users cannot post answers | Pending
Mobile UI | The website is responsive | Pending